Phoenix SIS

Solo Dev Sprint Plan

Modular Monolith Approach — SCRUM Master Edition

| Field | Value |
| --- | --- |
| Document Version | 1.0 |
| Date | July 13, 2026 (CST) |
| Developer | Patrick Hines (solo) |
| Approach | Modular monolith - one codebase, feature-flagged modules |
| Cadence | 2-week sprints (measured in hours, not days) |
| Total Hours (Estimate) | ~360-500 hours to Investor-Ready Prototype |
| Calendar Timeline | Ship when ready - no deadline pressure |
| Prior Context | Locked decisions: Hybrid architecture, self-host Ed-Fi, contribute back to Alliance |

# 1. The Strategy in One Page

## Modular Monolith - Why It Wins for Solo Dev

Instead of forking CMS into a separate Phoenix codebase, restructure the existing CMS solution into feature-flagged modules. One repo. One CI/CD. One Visual Studio solution. Different deployment configurations produce different products.

ONE REPOSITORY

(CaseManagementSystem)

│

┌──────────────────┼──────────────────┐

▼                  ▼                  ▼

Deployment A      Deployment B        Deployment C

(CMS-Prod)        (Phoenix-Dev)       (Phoenix-Demo)

PowerSchool: ON   PowerSchool: OFF    PowerSchool: OFF

Ed-Fi: OFF        Ed-Fi: ON           Ed-Fi: ON

Adult Ed: OFF     Adult Ed: ON        Adult Ed: ON

Portal: OFF       Portal: ON          Portal: ON

(Demo data loaded)

## The Four Guiding Principles

1. Sprints are boxes, not deadlines. A sprint is ~20-40 hours of Phoenix work, not 2 calendar weeks. Track hours, ship when the sprint's Definition of Done is met.

2. Every sprint produces something demoable. Record a 3-minute Loom at end of sprint. This maintains momentum across long timelines and becomes your investor pitch material.

3. Documentation is a deliverable, not a byproduct. When you return to Phoenix after 3 weeks on other projects, your prior self is a stranger. Write for that stranger.

4. Reversible decisions get made fast; irreversible ones get made carefully. Table names, folder structure = reversible, don't agonize. Ed-Fi namespace choices, data schema decisions = irreversible, get community input before committing.

# 2. The Module Map

Before writing any code, the CMS solution needs to be reorganized into feature-flagged modules. Some modules already exist (Advising); others are new (Ed-Fi, AdultEd, Portal). Every feature belongs to exactly one module.

## Modules Overview

| Module | Purpose | Status | Feature Flag |
| --- | --- | --- | --- |
| Core | Shared infrastructure - always on | Existing | N/A - always enabled |
| Advising | Case management (existing feature) | Existing | Advising:Enabled - default ON |
| PowerSchool | PowerSchool read/write integration | Existing | PowerSchool:Enabled - ON for CMS, OFF for Phoenix |
| EdFi | Ed-Fi ODS integration + sync | NEW | EdFi:Enabled - OFF for CMS, ON for Phoenix |
| AdultEd | Barriers, goals, PLA, competencies | NEW | AdultEd:Enabled - OFF for CMS, ON for Phoenix |
| Portal | Student-facing surface | NEW | Portal:Enabled - OFF for CMS, ON for Phoenix |
| Reports | Reports engine (existing) | Existing | Reports:Enabled - default ON |
| IdCard | ID card system (in-flight absorption) | In progress | IdCard:Enabled - varies |
| TimeClock | Time tracking (planned absorption) | Planned | TimeClock:Enabled - varies |

## Deployment Configurations

Three concrete deployment configurations you'll actually use:

| Config Name | Purpose | Feature Flags | Database | Deployed Where |
| --- | --- | --- | --- | --- |
| CMS-Prod | New Heights daily operations - untouched | PowerSchool ON, Advising ON, Reports ON, everything else OFF | CaseManagementDB (existing) | Azure App Service (existing) |
| Phoenix-Dev | Your development environment | PowerSchool OFF, EdFi ON, AdultEd ON, Portal ON, Advising ON | Local SQL Server Dev Edition | Your dev machine |
| Phoenix-Demo | Investor demos, later beta | Same as Phoenix-Dev, but with polished demo data | Azure SQL (~$15/mo) | Azure App Service |

# 3. Technology Decisions For Solo Dev

## Development Environment

| Decision | Choice | Why |
| --- | --- | --- |
| Local SQL Server | SQL Server 2022 Developer Edition on your Windows machine | Free. Zero cloud cost during dev. Full SQL Server feature set. |
| Ed-Fi ODS local | Docker container OR direct install on your dev machine | Ed-Fi ships Docker Compose files. Fastest path to local Ed-Fi. |
| Azure for Phoenix-Demo | Defer until you need to show investors | Save the ~$150/mo until you actually have a demo to host |
| On-prem SQL server | Skip unless you need multi-machine access | Weekend of setup work for zero prototype-stage benefit |
| Source Control | Existing GitHub repo, use branches | phoenix-dev branch is where Phoenix work happens; main stays CMS-Prod |
| CI/CD | Manual deploys during solo dev; automate when team hires | GitHub Actions can be added later; not worth investment now |

## Git Branch Strategy

Simple branching model that a SCRUM master will recognize:

main branch                    → CMS-Prod (untouched from Phoenix work)

│

├── phoenix-dev branch       → Phoenix development happens here

│     │

│     ├── feature/edfi-*     → Sprint feature branches

│     ├── feature/adulted-*  → Sprint feature branches

│     └── feature/portal-*   → Sprint feature branches

│

└── (occasional cherry-picks from phoenix-dev → main

when a general improvement should benefit CMS-Prod)

TAG strategy:

cms-v2.5.0    - CMS production release

phoenix-v0.1  - Phoenix prototype milestone

phoenix-v0.2  - Next milestone

...

Solo Dev Rule Never merge phoenix-dev to main. Phoenix work should ALWAYS be behind feature flags. If main accidentally deploys with Phoenix code, feature flags keep it dormant. This is the safety net for solo dev deployment mistakes.

# 4. The Backlog - Epics

Six epics, each broken into 2-week sprints. Total: 20-27 sprints = approximately 360-500 hours of Phoenix work. At varying velocity, that's 6-24 months of calendar time depending on your other commitments.

## Epic 1: Modular Refactor (4 sprints, ~80 hours)

Goal: Restructure CMS to support feature-flagged modules. Zero user-visible changes.

Value: Foundation for all future Phoenix work. Also incidentally improves CMS code health.

## Epic 2: Local Ed-Fi ODS Setup (2 sprints, ~40 hours)

Goal: Get Ed-Fi ODS running on your dev machine. Load Texas descriptors. Prove you can POST/GET students.

Value: Real Ed-Fi expertise. Discover unknowns before they become blockers.

## Epic 3: EdFi Module - Student Sync (4 sprints, ~80 hours)

Goal: Build the EdFi module. Sync students from local test data (or CMS Dev DB) into Ed-Fi ODS. Data quality dashboard.

Value: Prove the architecture. First demo-able Phoenix feature.

## Epic 4: AdultEd Module - First Extension (3 sprints, ~60 hours)

Goal: First adult-ed-specific feature end-to-end: Student Barriers. Data model + UI + reporting.

Value: The differentiation story becomes real. Submit to Ed-Fi Alliance for community feedback.

## Epic 5: Portal Module - MVP (6 sprints, ~120 hours)

Goal: Student-facing portal: login, view schedule, view credits/progress, view attendance, messaging placeholder.

Value: This is what investors will look at first. The visual proof that Phoenix exists.

## Epic 6: Investor-Ready Prototype (2 sprints, ~40 hours)

Goal: Polish. Demo data. Recorded walkthroughs. Pitch deck. Public-facing landing page.

Value: Investor readiness. Can begin capital conversations.

# 5. Sprint-by-Sprint Detail

How to Use This Section Each sprint is one 'card' with user stories, definition of done, estimated hours, and solo dev notes. Copy each sprint into your preferred backlog tool (Jira, Azure DevOps, GitHub Projects, even a Notion doc). Track hours to know your actual velocity.

EPIC 1 SPRINTS - Modular Refactor

Sprint 1: Feature Flag Foundation

Epic: Epic 1: Modular Refactor   |   Est. Hours: 15-20

Goal: Introduce a feature flag system that every module will use going forward.

User Stories:

- As a developer, I want a feature flag configuration in appsettings.json so I can enable/disable modules per deployment.

- As a developer, I want an IFeatureFlagService I can inject anywhere to check module state at runtime.

- As a developer, I want an admin page showing current feature flag state so I can verify deployment configuration.

Definition of Done:

- ✓ Features:Enabled section exists in appsettings.json with 8 module flags

- ✓ IFeatureFlagService interface + implementation registered in DI

- ✓ Admin page /admin/feature-flags shows current state (read-only in Phase 1)

- ✓ Docs: docs/features/feature-flags.md written

- ✓ 3-minute Loom recorded showing feature flag admin page

Solo Dev Notes: This is the smallest possible first sprint. Zero risk. Establishes rhythm. Prove your solo velocity before tackling bigger things.

Sprint 2: Wrap PowerSchool Module in Feature Flag

Epic: Epic 1: Modular Refactor   |   Est. Hours: 20-25

Goal: Retrofit PowerSchool integration with feature flag guards. Prove CMS-Prod is unaffected when flag stays ON.

User Stories:

- As a developer, I want all PowerSchool sync services to check the PowerSchool:Enabled flag before running.

- As a developer, I want PowerSchool-dependent Blazor pages to hide gracefully when the flag is off.

- As a developer, I want CMS-Prod deployment (with flag ON) to behave exactly as today.

Definition of Done:

- ✓ All PowerSchool sync services guarded by IFeatureFlagService.IsEnabled('PowerSchool')

- ✓ Manual test: turn PowerSchool:Enabled off in Phoenix-Dev - system continues running (with placeholder data)

- ✓ Manual test: New Heights production deploy has zero behavioral change

- ✓ Docs: docs/features/modules/PowerSchool.md written explaining the module boundary

- ✓ 3-minute Loom recorded showing feature flag toggle behavior

Solo Dev Notes: This is the moment of truth. If the PowerSchool module can be cleanly guarded, the modular monolith approach is validated. If not, back to design.

Sprint 3: Extract Advising Module Cleanly

Epic: Epic 1: Modular Refactor   |   Est. Hours: 20-25

Goal: Reorganize existing Advising code into a proper module structure matching the target pattern.

User Stories:

- As a developer, I want all Advising code in src/Modules/Advising/{Domain,Data,UI} following the established pattern.

- As a developer, I want the Advising module documented so I have a template for building new modules.

- As a developer, I want to verify no other module directly references Advising internals - only public interfaces.

Definition of Done:

- ✓ Advising code organized in Modules/Advising folder structure

- ✓ IAdvisingModule interface exposes public surface

- ✓ Static analysis (or manual review) confirms clean module boundaries

- ✓ Template document created: docs/features/modules/MODULE_TEMPLATE.md

- ✓ 3-minute Loom explaining the module structure

Solo Dev Notes: Advising is your best-understood module. Use this sprint to establish the pattern before applying it to new modules.

Sprint 4: Deployment Configuration System

Epic: Epic 1: Modular Refactor   |   Est. Hours: 15-20

Goal: Create the three deployment configurations (CMS-Prod, Phoenix-Dev, Phoenix-Demo) with distinct settings.

User Stories:

- As a developer, I want appsettings.CMS-Prod.json, appsettings.Phoenix-Dev.json, appsettings.Phoenix-Demo.json.

- As a developer, I want launchSettings.json profiles for each config so I can F5-run any of them.

- As a developer, I want a startup banner showing which config is running so I never confuse them.

Definition of Done:

- ✓ Three appsettings files exist with appropriate flag settings

- ✓ Visual Studio profiles let you switch between configs easily

- ✓ Startup banner in browser title AND admin pages shows current config

- ✓ Docs: docs/deployment/configurations.md explains each config's purpose

- ✓ 3-minute Loom showing switching between three configs

Solo Dev Notes: This is your safety net. If you can visibly see which config you're running, you can't accidentally deploy Phoenix-Dev to New Heights production.

EPIC 2 SPRINTS - Local Ed-Fi ODS Setup

Sprint 5: Ed-Fi ODS Local Deployment

Epic: Epic 2: Ed-Fi ODS Setup   |   Est. Hours: 20-30

Goal: Get Ed-Fi ODS running on your dev machine and reachable from Postman.

User Stories:

- As a developer, I want Ed-Fi ODS installed locally (Docker or direct install) so I have an API to talk to.

- As a developer, I want OAuth 2.0 client credentials configured so I can authenticate API calls.

- As a developer, I want to POST/GET a test student through the Ed-Fi API to confirm the round-trip.

Definition of Done:

- ✓ Ed-Fi ODS API running at http://localhost:port (documented)

- ✓ OAuth token acquisition works from Postman

- ✓ Test student created, retrieved, deleted through Postman

- ✓ Docs: docs/edfi/local-setup.md with EXACT setup steps (screenshots welcome)

- ✓ 3-minute Loom showing successful POST/GET/DELETE cycle

Solo Dev Notes: Expect to hit walls. Budget 30+ hours. This is where solo dev pain is highest. Post on community.ed-fi.org when stuck for more than 2 hours.

Sprint 6: Texas Descriptors + Sample Data

Epic: Epic 2: Ed-Fi ODS Setup   |   Est. Hours: 15-20

Goal: Load Texas-specific descriptors and Ed-Fi sample data. Prove the ODS is ready for real work.

User Stories:

- As a developer, I want Texas Ed-Fi extension descriptors loaded so PEIMS-relevant data has proper codes.

- As a developer, I want Ed-Fi sample data loaded so I have realistic students to test against.

- As a developer, I want a database backup/restore script so I can reset to clean state anytime.

Definition of Done:

- ✓ All Texas descriptors present (verified via API: GET /ed-fi/atRiskIndicatorDescriptors)

- ✓ Grand Bend sample data or Texas sample data loaded (~1000 students)

- ✓ PowerShell script: reset-edfi.ps1 restores to clean+descriptors state

- ✓ Docs: docs/edfi/reference-data.md explains descriptor namespaces

- ✓ 3-minute Loom showing sample student query

Solo Dev Notes: Ed-Fi Alliance publishes 'Grand Bend' and 'Northridge' sample data sets. Also TEA publishes Texas-specific samples. Use both.

EPIC 3 SPRINTS - EdFi Module + Student Sync

Sprint 7: EdFi Module Scaffold + API Client

Epic: Epic 3: EdFi Module   |   Est. Hours: 20-25

Goal: Create the EdFi module in the solution. Build a working Ed-Fi API client with auth and retry logic.

User Stories:

- As a developer, I want src/Modules/EdFi/{Domain,Data,UI,Services} following the module template.

- As a developer, I want an IEdFiApiClient with strongly-typed methods for common resources.

- As a developer, I want automatic OAuth token refresh with caching so I don't manage tokens manually.

Definition of Done:

- ✓ EdFi module compiles and is referenced by CaseManagement.Web

- ✓ IEdFiApiClient supports GetStudent, PostStudent, GetStudents (list)

- ✓ Polly retry policy handles transient failures

- ✓ Integration test hits local Ed-Fi ODS successfully

- ✓ Docs: docs/features/modules/EdFi.md

- ✓ 3-minute Loom showing test project calling Ed-Fi API

Solo Dev Notes: Use NSwag or Refit to generate strongly-typed clients from the Ed-Fi Swagger spec. Manual DTOs are a maintenance burden you don't want alone.

Sprint 8: Student Identity Model

Epic: Epic 3: EdFi Module   |   Est. Hours: 15-20

Goal: Design and implement the Phoenix student identity model with mapping to external systems.

User Stories:

- As a system, I want a Phoenix-issued StudentUniqueId format independent of any source system.

- As a developer, I want a StudentIdentityMap table linking Phoenix IDs to external system IDs (PS, Ascender, etc.).

- As a developer, I want a service that generates the next Phoenix StudentUniqueId per tenant.

Definition of Done:

- ✓ Phoenix_StudentIdentityMap table created via EF migration

- ✓ IStudentIdentityService.GetOrCreatePhoenixId(externalSystem, externalId) implemented

- ✓ Unit tests cover collision handling and idempotency

- ✓ Docs: docs/edfi/student-identity.md

- ✓ 3-minute Loom showing identity map records

Solo Dev Notes: This is architecturally important. Once IDs are issued, they're forever. Design carefully. Ask Claude to review before committing.

Sprint 9: First Student Sync - CMS to Ed-Fi

Epic: Epic 3: EdFi Module   |   Est. Hours: 25-30

Goal: Sync a subset of CMS students into local Ed-Fi ODS. Prove the transformation pipeline works.

User Stories:

- As a developer, I want to POST 10 CMS test students into Ed-Fi ODS with all required fields populated.

- As a developer, I want a descriptor mapping service that translates CMS codes to Ed-Fi descriptor URIs.

- As a developer, I want a sync log showing what was synced, when, and any errors.

Definition of Done:

- ✓ Manual test: 10 students appear in local Ed-Fi ODS with correct data

- ✓ Phoenix_EdFiSyncLog table + logging in place

- ✓ IStudentSyncService.SyncBatch(students) implemented and tested

- ✓ Descriptor mapping covers at minimum: race, ethnicity, sex, grade level, campus

- ✓ Docs: docs/edfi/student-sync.md

- ✓ 3-minute Loom showing sync running end-to-end

Solo Dev Notes: This is your 'aha' moment. If this sprint succeeds, the whole architecture is validated. Celebrate accordingly.

Sprint 10: Data Quality Dashboard

Epic: Epic 3: EdFi Module   |   Est. Hours: 20-25

Goal: Build a UI showing sync health, data drift, and error rates.

User Stories:

- As an admin, I want to see how many students are in Ed-Fi vs CMS at a glance.

- As an admin, I want to see recent sync errors so I can investigate.

- As an admin, I want to see fields where CMS and Ed-Fi disagree so I can find data quality issues.

Definition of Done:

- ✓ Admin page /admin/edfi/health shows sync summary

- ✓ Admin page /admin/edfi/errors shows last 50 sync errors with details

- ✓ Admin page /admin/edfi/drift shows students where CMS and Ed-Fi disagree

- ✓ Docs: docs/features/modules/EdFi.md updated with dashboard usage

- ✓ 3-minute Loom demoing dashboard

Solo Dev Notes: First truly Phoenix-visible UI. This is what you'll show anyone who asks 'what does Phoenix look like?' before the portal exists.

EPIC 4 SPRINTS - AdultEd Module First Feature

Sprint 11: StudentBarrier Data Model + API

Epic: Epic 4: AdultEd Module   |   Est. Hours: 20-25

Goal: First adult-ed-native feature. Design StudentBarrier table, service layer, and REST endpoints.

User Stories:

- As a case manager, I want to record structured barriers a student faces (housing, childcare, transportation, mental health, justice-involved, etc.).

- As a case manager, I want each barrier to have status (Active/Resolved), severity, notes, and creation date.

- As a developer, I want a REST API for barriers so both the staff UI and eventual portal can use it.

Definition of Done:

- ✓ AdultEd_StudentBarrier table created via EF migration

- ✓ AdultEd_BarrierType reference table with 10 initial barrier types

- ✓ IBarrierService with CRUD operations

- ✓ REST API: GET/POST/PUT/DELETE /api/adulted/students/{id}/barriers

- ✓ Unit tests for service layer

- ✓ Docs: docs/features/modules/AdultEd/barriers.md

- ✓ 3-minute Loom showing Postman calls

Solo Dev Notes: This becomes the reference implementation for the first Ed-Fi Alliance contribution. Design carefully. Model after other Ed-Fi extensions you find in the community.

Sprint 12: StudentBarrier UI (Staff-Facing)

Epic: Epic 4: AdultEd Module   |   Est. Hours: 20-25

Goal: Blazor UI for case managers to view and manage student barriers.

User Stories:

- As a case manager, I want to see a student's active barriers on their profile page.

- As a case manager, I want to add, edit, resolve, and delete barriers with notes.

- As a case manager, I want a filter to show only students with specific barriers.

Definition of Done:

- ✓ New tab on StudentProfile page: 'Barriers'

- ✓ Modal for add/edit barrier with dropdown for type

- ✓ New report: 'Students by Barrier Type'

- ✓ Barrier count badge on student list views

- ✓ 3-minute Loom showing barrier workflow

Solo Dev Notes: Reuse existing Blazor page patterns from Advising module. Don't reinvent UI conventions.

Sprint 13: Ed-Fi Extension Draft + Community Submission

Epic: Epic 4: AdultEd Module   |   Est. Hours: 15-20

Goal: Formalize StudentBarrier as an Ed-Fi extension proposal. Submit to community for feedback.

User Stories:

- As Phoenix SIS product, I want a formal extension spec that could become part of Ed-Fi standard.

- As a community member, I want to post my extension proposal on community.ed-fi.org for feedback.

- As a developer, I want to iterate the schema based on early feedback.

Definition of Done:

- ✓ Formal extension spec: docs/ed-fi-extensions/ael-StudentBarrier-v0.1.md

- ✓ XML/JSON sample records

- ✓ Community forum post created

- ✓ Initial response gathered (may take weeks - not blocking)

- ✓ 3-minute Loom explaining the extension

Solo Dev Notes: This is your first public-facing Phoenix content. Ed-Fi community will notice. Represents Phoenix well.

EPIC 5 SPRINTS - Portal MVP

Sprint 14: Portal Framework Decision + Scaffold

Epic: Epic 5: Portal MVP   |   Est. Hours: 20-25

Goal: Decide portal tech stack. Scaffold the portal project. Basic auth working.

User Stories:

- As a solo dev, I want to make an informed decision on portal tech (Blazor vs Next.js vs Blazor United).

- As a developer, I want a working portal project with login page hitting existing Entra AD.

- As a student, I want to log in and see a placeholder 'Welcome' page.

Definition of Done:

- ✓ Decision document: docs/portal/tech-stack-decision.md

- ✓ Portal project scaffolded (whichever framework chosen)

- ✓ Login flow works with Entra AD (student accounts)

- ✓ Placeholder home page loads after login

- ✓ 3-minute Loom showing login flow

Solo Dev Notes: Given solo dev constraints, Blazor Server (matching CMS) is probably right. Blazor United (server+client hybrid) is worth investigating. Next.js means learning JavaScript ecosystem alone.

Sprint 15: Portal - My Schedule

Epic: Epic 5: Portal MVP   |   Est. Hours: 20-25

Goal: Student can view their current class schedule.

User Stories:

- As a student, I want to see today's classes with times and rooms.

- As a student, I want to see this week's schedule at a glance.

- As a student, I want the schedule to work on my phone.

Definition of Done:

- ✓ Mobile-responsive schedule view

- ✓ Today and Week views

- ✓ Data sourced from Ed-Fi ODS (or PS cache during transition)

- ✓ 3-minute Loom on both desktop and mobile

Sprint 16: Portal - My Progress

Epic: Epic 5: Portal MVP   |   Est. Hours: 25-30

Goal: Student can see credits earned, credits remaining, projected graduation.

User Stories:

- As a student, I want to see how many credits I've earned so I know how close I am to graduating.

- As a student, I want to see what classes I still need.

- As a student, I want a visual progress indicator (percent to graduation).

Definition of Done:

- ✓ Progress page with visual progress bar

- ✓ Credit-by-subject-area breakdown

- ✓ Remaining requirements list

- ✓ 3-minute Loom showing progress view

Solo Dev Notes: This is the most emotionally powerful screen for adult learners. Get the UX right. Iterate.

Sprint 17: Portal - My Attendance

Epic: Epic 5: Portal MVP   |   Est. Hours: 15-20

Goal: Student can see their attendance rate and history.

User Stories:

- As a student, I want to see my attendance rate this term.

- As a student, I want to see specific dates I was absent or tardy.

- As a student, I want to know if my attendance is at risk of causing problems.

Definition of Done:

- ✓ Attendance dashboard with rate visualization

- ✓ History table showing dates and codes

- ✓ Warning indicator when attendance dips below threshold

- ✓ 3-minute Loom

Sprint 18: Portal - Messages & Announcements

Epic: Epic 5: Portal MVP   |   Est. Hours: 25-30

Goal: Student can receive messages from staff and school-wide announcements.

User Stories:

- As a student, I want to receive messages from my teachers and case manager.

- As a student, I want to see school-wide announcements.

- As a student, I want to mark messages as read.

- As a case manager, I want to send a message to my students through the portal (staff-side UI in this sprint).

Definition of Done:

- ✓ Portal_Message table via EF migration

- ✓ Student can view messages

- ✓ Staff can send messages

- ✓ Read/unread state tracked

- ✓ Announcements broadcast to filtered groups

- ✓ 3-minute Loom

Sprint 19: Portal - Absence Requests + Service Requests

Epic: Epic 5: Portal MVP   |   Est. Hours: 20-25

Goal: Student can submit an absence request or request a support service.

User Stories:

- As a student, I want to submit an absence request for a future date with reason.

- As a student, I want to request help (childcare, transportation, food) through the portal.

- As staff, I want to see incoming requests and approve/route them.

Definition of Done:

- ✓ Portal_AbsenceRequest and Portal_ServiceRequest tables

- ✓ Student submission forms

- ✓ Staff review queue

- ✓ Notification to requester when status changes

- ✓ 3-minute Loom

EPIC 6 SPRINTS - Investor-Ready Prototype

Sprint 20: Polish + Demo Data

Epic: Epic 6: Investor-Ready Prototype   |   Est. Hours: 25-30

Goal: Polish rough edges. Load realistic demo data. Deploy Phoenix-Demo to Azure.

User Stories:

- As a demo viewer, I want to see realistic (not lorem ipsum) student data.

- As a demo viewer, I want a landing page explaining what Phoenix SIS is.

- As a solo dev, I want to host Phoenix-Demo somewhere investors can access it 24/7.

Definition of Done:

- ✓ 50-100 fake but realistic students in Phoenix-Demo

- ✓ Landing page at phoenix-sis.com or similar

- ✓ Azure deployment of Phoenix-Demo

- ✓ Demo user accounts with README on how to access

- ✓ 3-minute polished demo video

Solo Dev Notes: Investors will decide in the first 30 seconds. Landing page + first screen matter more than any feature.

Sprint 21: Pitch Materials + Documentation

Epic: Epic 6: Investor-Ready Prototype   |   Est. Hours: 20-25

Goal: Create investor pitch deck, one-pager, and public documentation.

User Stories:

- As an investor, I want a 10-slide pitch deck explaining the opportunity.

- As an investor, I want a one-page executive summary I can share with partners.

- As a prospective customer, I want public docs explaining the product.

Definition of Done:

- ✓ 10-slide pitch deck (Google Slides / PowerPoint)

- ✓ 1-page PDF one-pager

- ✓ docs/README.md as public documentation entry point

- ✓ Blog post: 'Why We Built Phoenix SIS' (personal narrative)

Solo Dev Notes: You have this document series (Design Conversation, Fit Assessment, Architecture Doc, Sprint Plan) - repurpose ruthlessly into pitch content.

# 6. Solo Dev Operating Model

## Weekly Rhythm

SCRUM ceremonies adapted for solo:

| Ceremony | Solo Adaptation | Time |
| --- | --- | --- |
| Daily Standup | Weekly Loom recording: what did I do, what's next, blockers | 30 min / week |
| Sprint Planning | Every 2 weeks (of active Phoenix work): review backlog, pick sprint goal | 45 min |
| Sprint Review | Loom demo at end of each sprint | 20 min |
| Sprint Retro | Bi-weekly written retro (5 questions in a template) | 20 min |
| Backlog Grooming | Monthly - review and re-prioritize backlog | 45 min |

## Definition of Sprint Complete

A sprint is complete when ALL of these are true:

- All planned user stories meet their Definition of Done

- 3-minute Loom demo recorded and saved

- Documentation added or updated in /docs

- Git tag pushed: phoenix-sprint-{N}

- Sprint retro written (even 5 sentences)

- Next sprint's goal and stories drafted

## When Life Interferes

Rules for handling the reality of variable-time solo dev:

- Sprint pause: If you can't touch Phoenix for 2+ weeks, formally pause the sprint. Update your tracker with 'PAUSED - resuming when [event]'. Prevents ambiguity when returning.

- Sprint cancel: If a sprint is 50% done and priorities changed, cancel remaining stories cleanly. Move to next sprint's backlog. Don't leave partial work sitting.

- Return-from-hiatus ritual: After a break of 2+ weeks, spend the first hour re-reading your last sprint's retro + docs. Watch your last Loom. Do NOT start coding immediately.

- Feature flag as safety net: In-progress features live behind sub-flags. Never commit half-done work to main. Always leave Phoenix in a working state at end of each work session.

# 7. Solo Dev Risk Register

Specific risks that emerge from solo-dev constraints:

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Motivation dip after 3-6 months | High | High | Ship visible demos every sprint. Share Looms with a mentor/spouse/friend for external accountability. |
| Solo dev architecture mistakes (Ed-Fi patterns) | High | Medium | Community forum for critical decisions. Have Claude review data model designs before committing. |
| Life event disrupts 2+ months of work | Medium | Medium | Modular monolith means Phoenix can sit dormant safely. Feature flags off = normal CMS. |
| CMS work overwhelms Phoenix work | High | High | Time-box CMS commitments. Block Phoenix time on calendar. Say no to non-critical CMS features. |
| Ed-Fi learning curve blocks a sprint | High | Medium | Community forum. Claude. Read code samples from other Ed-Fi implementers on GitHub. |
| Investor timing mismatch (ready before or after market) | Medium | High | Ship 'good enough' investor prototype at sprint 21. Don't gold-plate before showing to investors. |
| IP/employment conflict with day job | ? | Very High | Talk to a lawyer NOW. Get written work-for-hire clarification. IP contamination kills companies. |
| Burnout from too many parallel projects | Medium | High | Explicit weekly hour targets per project. Recovery weeks with zero Phoenix work are OK and encouraged. |

# 8. Infrastructure Plan

## Phases 1-4 (Sprints 1-13): Everything Local

Your dev machine + SQL Server Developer Edition + local Ed-Fi ODS. Zero cloud spend.

| Component | Where | Cost |
| --- | --- | --- |
| SQL Server | SQL Server 2022 Developer Edition on your dev machine | $0 |
| Ed-Fi ODS | Docker Compose or direct install on your dev machine | $0 |
| CMS-Prod | Existing Azure infrastructure (unchanged) | Existing |
| Phoenix-Dev | Your dev machine only | $0 |
| Source control | Existing GitHub | $0 |

## Phase 5 (Sprints 14-19): Portal Demo Access

When you want to show a friend or advisor the portal, you'll need it hosted somewhere accessible. Add minimal Azure:

| Component | Where | Cost |
| --- | --- | --- |
| Phoenix-Demo App Service | Azure App Service B1 tier | ~$15/mo |
| Phoenix-Demo SQL | Azure SQL Basic tier | ~$5/mo |
| Custom domain (optional) | phoenix-sis.com registration | ~$15/yr |

## Phase 6 (Sprints 20-21): Investor-Ready

Same as Phase 5, but consider adding:

- Application Insights for observability (~$10/mo)

- Backup automation

- Custom domain with SSL

## On-Prem Hardware Recommendation

Verdict: Don't build the on-prem server for prototype. Reasoning: (1) A weekend of setup work delays Sprint 1. (2) You lose Phoenix access when you're not home. (3) You're the only user; single-machine dev is fine. Reconsider on-prem when you have a partner developer or need shared team access.

# 9. Immediate Next Actions

## This Week

- Read this document twice

- Set up your solo backlog tool (GitHub Projects recommended - free, git-native)

- Copy Sprint 1 stories into your tracker

- Register on community.ed-fi.org

- Bookmark techdocs.ed-fi.org

- Block calendar time for Phoenix work (even if it's just 2 hours)

## Before Starting Sprint 1

- Talk to a lawyer about IP/employment (do NOT skip this)

- Confirm SQL Server 2022 Developer Edition is installed locally

- Create Loom or similar screen recording setup

- Create a Phoenix-specific email or communication channel (separate from personal/work)

## Sprint 1 Kickoff Checklist

- Have you read the Feature Flag pattern in Microsoft docs?

- Do you have 15+ hours available in the next 2 weeks?

- Is your development environment ready?

- Have you decided which backlog tool you'll use?

This is your operating plan. It's designed for the reality of solo development, variable time, and no fixed deadline. Trust the modular monolith approach - it's the right call. Take the sprints in order. Ship every sprint. And keep the Looms - they're your investor pitch material building itself.

# Appendix A: Sprint Retro Template

Use this 5-question template at the end of every sprint. Takes 15 minutes. Compounds enormously over time.

# Sprint {N} Retro - {Date}

## What went well?

-

## What was harder than expected?

-

## What did I learn?

-

## What will I do differently next sprint?

-

## Sprint hours actual vs. estimated?

Estimated: X hours

Actual: Y hours

Variance reason:

# Appendix B: Story Card Template

Standard template for adding new stories to the backlog:

# Story: {short name}

**Epic:** {which epic}

**Sprint:** {planned sprint number or 'backlog'}

**Estimate:** {hours}

## User Story

As a {role}, I want {feature} so that {benefit}.

## Acceptance Criteria

- Given {context}, when {action}, then {outcome}

-

## Definition of Done

- [ ] Code compiles and runs

- [ ] Documentation updated

- [ ] Manual test performed

- [ ] Feature flag guard verified (if new feature)

## Dependencies

-

## Notes

-